Northeastern University & OMSiH Internal Meeting

Friday, February 6, 2015

Conference Call

| One Million Solutions in Health | Northeastern University |
| --- | --- |
| Dawn Van Dam Brett Johnson | Ahmed Busnaina (absent) Eric Howard Cihan Yilmaz |

Agenda:

- Grants

- TEC Project: Compounds

- Signature Square Webinar

- Diagnostics and Devices Steering Committee

- Business Development Meeting

I) Grants

Ahmed made the decision not do the February grant.

Cihan is working on the March grant.

II) TEC Projects: Compounds

Cihan has the Acetaminophen and is solubilizing it. He is working on a study design so that we can circulate it.

Exenatide is an AstraZenaca drug not a Pfizer drug, and for them to purchase would be very expensive -  $500/mg.  Mark found someone in cardiovascular who manufactures the peptides in-house. It will be sorted out soon, so the process of sending the drugs out has taken longer than expected, about a week behind original plan.

III) Signature Square Webinar

A date for the webinar still needs to be finalized. The potential dates are  March: 3rd, 4th or 5th . We do need 6 weeks to promote it, so if we don’t have a date locked down soon we will likely need to push it back.

Because it looks like Ahmed has availability is good for the week of March 10th, Dawn recommends we try for that week.

Eric is going to take the lead on finding who the speaker will be for the webinar, so we can firm up a date and time and get an abstract out to promote it.

IV) Diagnostics and Devices Steering Committee

Ahmed will put together a list of people for OMSiH to reach out to, as potential candidates for the Steering Committee.

Scott from GE was a recommendation from Ahmed.  Eric will send Scott’s contact information to Brett.

V) Business Development Meeting

Brett is trying to schedule an in-person meeting next week with Cihan, Ahmed and the other founder of Biolome.

Action Items

- Eric to send Brett Scott’s contact information (from GE), in order to get him involved in the Signature Square project

- Ahmed to confirm the date of the next Signature Square webinar

- Brett to confirm a face- to-face meeting with Ahmed, Cihan and the other founder of Biolome.